## ToDo
feature | component | target | log diff | tech diff | status | priority | severity
The content of this file will be moved to the BugTracker of MV.net in the future.
http://www.mariovaldez.net/webapps/bugtracker/
More languages. | Languages | Constant | 2 Difficult (Requires hard-to-get resources) | 7 Too easy (Requires minor changes in content) | 3 Implementing / Executing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem)
CMS API cleaning. | CodeBase | Constant | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 3 Implementing / Executing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
General cleaning / commenting of code. | CodeBase | Constant | 3 Average (Requires available resources) | 6 Very easy (Requires minor coding) | 3 Implementing / Executing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Per-user preferences. | Lib | v0.6.4 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 2 Designing / Preparing | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem) | Field list | Priority list | Status list | Severity list
User manual (Spanish/English). | Documentation | v0.6.4 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 3 Implementing / Executing | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem) | Component | 1 Highest priority | 1 Evaluating / Thinking | 1 Blocker (Blocks development of other features)
Revision control/versioning. | StorageModel | v0.6.4 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem) | Target | 2 High priority | 2 Designing / Preparing | 2 Critical (Crashes, loss of data, security problems)
RDF/RSS export syndication | Renderer | v0.6.4 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 2 Designing / Preparing | 4 Low priority | 7 Enhancement (Request for enhancement) | Status | 3 Medium priority | 3 Implementing / Executing | 3 Major (Major lack of function, most requested feature, major usability problem)
Approval path. | Workflow | v0.6.6 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 2 Designing / Preparing | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem) | Severity | 4 Low priority | 4 Testing / Reviewing | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Setup environment checking. | Setup | v0.6.6 | 3 Average (Requires available resources) | 8 Unknown | 2 Designing / Preparing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) | Priority | 5 Lowest priority | 5 Completed | 5 Minor (Lack of function with easy workaround, minor usability problem)
Language/charset selectable per document. | Charset control | v0.6.6 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 4 Low priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  |  |  | 6 Trivial (Cosmetic problem)
Security review to current code base. | Security | v0.6.8 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 3 Implementing / Executing | 2 High priority | 2 Critical (Crashes, loss of data, security problems) |  |  |  | 7 Enhancement (Request for enhancement)
Formal definition of CMS API. | CodeBase | v0.6.8 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 3 Implementing / Executing | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Several viewer groups per document. | StorageModel | v0.6.8 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 1 Evaluating / Thinking | 3 Medium priority | 5 Minor (Lack of function with easy workaround, minor usability problem)
Content-change notifications (email, report, summary page, etc). | Creation/edition | v0.7.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 1 Evaluating / Thinking | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Themes support and template tranformations. | Renderer | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Context sensitive help. | OnlineHelp | v0.7.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Integration with WAP module. | Renderer | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Document archiving | StorageModel | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 2 Designing / Preparing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  | Target list | Perceived technical difficulty
Third-party Java-based HTML editor. | WYSIWYG | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  | v0.6.0 | 1 Too difficult (Requires changes in architecture, API functions or database fields usage affecting other modules and backward compatibility)
WebDav interface | Renderer/Filrman | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 3 Medium priority | 7 Enhancement (Request for enhancement) |  | v0.6.2 | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.)
XMLRPC functions for document management | Lib/CodeBase | v0.7.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v0.6.4 | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.)
Variant of #ALBUM x y# | WMParser | v0.7.0 | 3 Average (Requires available resources) | 5 Easy (Requires single module recoding) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v0.6.6 | 4 Average (Requires creating API functions or single module coding or single unit testing)
PGP/SMIME signature attachement and verification. | Signatures | v0.7.6 | 3 Average (Requires available resources) | 8 Unknown | 2 Designing / Preparing | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem) |  | v0.6.8 | 5 Easy (Requires single module recoding)
Backup (files/metadata) | DBPipes/StorageModel | v0.7.6 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem) |  | v0.7.0 | 6 Very easy (Requires minor coding)
Content replication | DBPipes/StorageModel | v0.7.6 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v0.7.6 | 7 Too easy (Requires minor changes in content)
Consistency-fixing tool. | Checker | v0.8.0 | 3 Average (Requires available resources) | 8 Unknown | 2 Designing / Preparing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  | v0.8.0 | 8 Unknown
Expiration time for content. | Renderer | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 2 Designing / Preparing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  | v0.8.6
Repetition schedule for cyclic content. | Renderer | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 2 Designing / Preparing | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem) |  | v0.9.0
Richer support in the wikimarkup. | WMParser | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 1 Evaluating / Thinking | 4 Low priority | 5 Minor (Lack of function with easy workaround, minor usability problem) |  | v0.9.6
More complex statistics. | Stats | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v1.0.0
Preindexing of content for search. | Search | v0.8.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v1.0.6 | Perceived logistic difficulty
Preindexing of file content for search. | Search | v0.8.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | v1.1.0 | 1 Very difficult (Requires unavailable or too-costly resources)
Upload to central image repository. | Images | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  | Constant | 2 Difficult (Requires hard-to-get resources)
Upload to central file repository. | FileMan | v0.8.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement) |  |  | 3 Average (Requires available resources)
Multiple-language content versions. | StorageModel | v0.9.0 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem) |  |  | 4 Easy (Requires very available resources)
Abstraction of DB function calls (to work without Phprojekt). | Lib | v0.9.0 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem) |  |  | 5 Very easy (Requires already acquired or used resources)
Abstraction of login/users/groups function calls (to work without Phprojekt). | Lib/Permissions | v0.9.0 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem) |  |  | 6 Unknown
Abstraction of login/users/groups function calls (to work with other user/group databases). | Lib | v0.9.0 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 2 Designing / Preparing | 3 Medium priority | 3 Major (Major lack of function, most requested feature, major usability problem)
XML content support. | StorageModel | v1.0.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Weighted-ranking and spatial restriction for the search. | Search | v1.0.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Language selection in setup scripts. | Setup | v1.0.0 | 3 Average (Requires available resources) | 5 Easy (Requires single module recoding) | 2 Designing / Preparing | 4 Low priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Context sensitive menus. | OnlineHelp | v1.0.0 | 3 Average (Requires available resources) | 2 Very difficult (Requires changes in architecture, API functions or database fields usage affecting other modules. Or requires too extensive work.) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Database access optimization. | DBPipes | v1.0.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Mass-importer to manage legacy data. | Creation/edition | v1.0.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Mass-importer to manage prebuild repositories. | Creation/edition | v1.0.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
ACL permissions. | Security | v1.1.0 | 3 Average (Requires available resources) | 1 Too difficult (Requires changes in architecture, API functions or database fields usage affecting other modules and backward compatibility) | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
External link checker. | Checker | v1.1.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Public site view. | Renderer | v1.1.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Rewrite the wikimarkup parser. | WMParser | v1.1.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
Static export. | Export | v1.1.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 4 Low priority | 7 Enhancement (Request for enhancement)
MS Word/OO Writer macro support (for edition). | Creation/Edition | v1.1.0 | 3 Average (Requires available resources) | 8 Unknown | 1 Evaluating / Thinking | 5 Lowest priority | 7 Enhancement (Request for enhancement)

## Done
feature | component | target | log diff | tech diff | status | priority | severity
Color picker for HTML editor. | WYSIWYG | v0.6.0 | 3 Average (Requires available resources) | 8 Unknown | 5 Completed | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem)
All HTML code should be part of CSS classes. | CodeBase | v0.6.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 5 Completed | 2 High priority | 3 Major (Major lack of function, most requested feature, major usability problem)
Pagination for user comments. | UserComments | v0.6.0 | 3 Average (Requires available resources) | 5 Easy (Requires single module recoding) | 5 Completed | 2 High priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
PhpInfo output in setup/config scripts. | Setup | v0.6.0 | 3 Average (Requires available resources) | 5 Easy (Requires single module recoding) | 5 Completed | 2 High priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Form to setup syndication news management. | News | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Content-less documents (only title+summary). | Renderer | v0.6.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Displaying of historical ratings/comments (even if currently disabled). | Renderer | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Special announce document type. | Renderer | v0.6.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
File/image-uploading in HTML editor. | WYSIWYG | v0.6.0 | 3 Average (Requires available resources) | 3 Difficult (Requires changes in API functions or database fields usage or changes in other modules, affecting other modules. Or requires extensive testing/review.) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Midas extensions (mozilla) for HTML editor. | WYSIWYG | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 3 Medium priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Improve usability of configuration page (use drop-lists, not fields; show default values). | Setup | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 3 Medium priority | 5 Minor (Lack of function with easy workaround, minor usability problem)
Links in setup page and console page. | Setup | v0.6.0 | 3 Average (Requires available resources) | 5 Easy (Requires single module recoding) | 5 Completed | 3 Medium priority | 7 Enhancement (Request for enhancement)
Variant of #INDEX x# | WMParser | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 3 Medium priority | 7 Enhancement (Request for enhancement)
Richer file operations (rename, duplicate, compress, etc). | FileMan | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 4 Low priority | 4 Normal (Lack of function with workaround, often requested feature, medium usability problem)
Images and logos for index pages. | Renderer | v0.6.0 | 3 Average (Requires available resources) | 4 Average (Requires creating API functions or single module coding or single unit testing) | 5 Completed | 4 Low priority | 7 Enhancement (Request for enhancement)